## Slide 1: Preparation at Subaru/Summit before delivery of subsystems
Atsushi Shimono
(2015/11/27)
PFS Software team Study Note : SSN-00020-001

## Slide 2: Outline
This note is a summary of items to be done at Subaru/Summit before receiving subsystems from institutions, in electronics and software point of view. Aim of this summary is to show hardware need to be purchased or delivered at certain epochs for the project and Subaru, but will not include any software module (which will not have highly solid delivery date…). Also connections or power supplies required will be shown per each setup.
Items and assigned delivery, with who will (or is assumed to) procure
MCS at 2016/08
SCR at 2017/06
SM1,2 at 2017/08
PFI at 2018/02

## Slide 3: Items and assigned delivery
Followings are hardware items which the project (or Subaru) need to prepare or deliver to the summit, and subsystems use these items.
CB2F (Control Building 2F)
  Rack to host items (Subaru): before all of followings
    Assumed deepest unit is ~760mm (MPS), ~650mm (DB host)
  Network switch (IPMU; already in hand): (at least) 1 at MCS, 2nd at SCR
  ICS RAID6 storage (IPMU; already in hand): SM1
    MCS backup could be done with small storage?
  VM host computers (IPMU; some already in hand)
    (at least) 1 at MCS (any subsystem delivered to summit) – to run MHS
    Others depends on system load
  Serial communication (MLP1; IPMU) host: PFI
  KVM, PDU etc. (IPMU; some already in hand): MCS?
  DB host (IPMU; spec TBD): SM1??
SpS (both IR3 and TUE-IR)
  5th rack (from JHU): SCR
  Network switch to connect CB2F (IPMU; already in hand): SCR
  UPS and power supply (Subaru): SCR
  1U host computer @ 5th rack (IPMU; spec TBD): SCR
  Telemetry devices/system (TBD): SCR (or SM1)

## Slide 4: Setup to accept MCS
MCS will be installed as Cs instrument. We need to have minimum operation hardware at CB2F, including PFS network.
19inch Rack (Subaru)
PFS network switch (at least 1; IPMU; already in hand)
  Also connection to subaru’s core switch
VM host (IPMU; 1 already in hand)
  Hosting administrative VM, e.g. dnsmasq
KVM, PDU (IPMU; already in hand)
At this stage, no special care for power distribution is required, only like connecting things to PDU at CB2F. Also network is simple, we need two fiber connection to Cs and its standby (one active, one backup), one connection to subaru core switch with routing.

## Slide 5: Setup to accept SCR
In parallel to build SCR (Spectrograph Clean Room) at TUE-IR (IR4), we need to have control hardware for SCR.
2nd network switch at CB2F (IPMU; already in hand)
  might only need 1 SFP to SpS, but better to have and check working at this moment
Network switch at SpS (IPMU; already in hand)
5th rack (from JHU)
UPS at IR3, with power distribution/panel (Subaru)
1U host computer (also for SCR control) (IPMU)
Telemetry devices (TBD)
  e.g. Lakeshore temperature monitor and sensors
At this point, we need full power distribution system to supply spectrograph, both UPS and power panel w/ cables. Environment active control subsystem for SCR shall be considered as a part of SCR, so not listed here.
For network and storage, we only need “connected” at this point, so performance evaluation on network in parallel to SCR preparation (or validation) is fine.

## Slide 6: Setup to accept SM1,2
Before we have SM1,2 at summit, we need almost all of hardware.
ICS RAID6 storage (IPMU)
DB host (IPMU)
  Not as full operation (e.g. interaction with ETS or survey coordination), but to store MHS status archive or telemetry etc.
Before this point, PFS network and storage need to be fully prepared and validated on performance point of view (for NCU1,2 operation).

## Slide 7: Setup to accept PFI
Most of computing and power resources need to be active well before delivery of PFI to the summit.
Serial communication (IPMU)
  This communication will be validated at factory of melco (Mitsubishi; at Amagasaki) in test setup.